Milestones

2023-02-26 Choose a project proposal and send your choice via email to epsatisep@gmail.com

2023-03-08 Define the Project Backlog (what must be done and key deliverables - every member should preferably participate in every task), Global Sprint Plan, Initial Sprint Plan (which tasks should be included, who does what) and Release Gantt Chart of the project and insert them on the wiki (planning)

2023-03-15 Upload the “black box” System Diagrams & Structural Drafts to the wiki

2023-03-22 Upload the List of Components and Materials (what & quantity) to the wiki

2023-03-29 Upload the detailed System Schematics & Structural Drawings to the wiki and do the cardboard scale model of the structure

2023-04-16 Upload the Interim Report and Presentation to the wiki. The report must contain the the following chapters: Introduction, Project Management, State of the Art, Marketing Plan, Eco-efficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography. In particular, the Project Management chapter includes the updated project progress register, the sprint report for completed sprints (tasks that were included, statuses, assignees, allocations) and the updated release Gantt chart

2023-04-20 Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks

2023-04-26 Upload the final List of Materials (local providers & price, including VAT and transportation), and 3D model video to the wiki

2023-05-07 Upload refined Interim Report (based on Teacher & Supervisor Feedback)

2023-05-24 Upload packaging solution to Deliverables and Report

2023-06-31 Upload the results of the Functional Tests to the wiki

2023-06-18 Upload the Final Report, Presentation, Video, Paper, Poster and Manual

2023-06-22 Final Presentation, Individual Discussion and Assessment (reserve the whole day)

2023-06-27:

Update the wiki, report, paper with all suggested corrections

Place in the files section of the MS Teams channel of your team a folder with the refined deliverables (source + PDF) together with all code and drawings produced

Hand in to the EPS coordinator a printed copy of the refined report and poster

2023-06-29:

Hand in the prototype and user manual to the client

Receive the EPS@ISEP certificate

Bring typical food from your country

Project Plan

Sprint	Start	Finish
Row 1 Col 1	Row 1 Col 2	Row 1 Col 3
Row 2 Col 1	d
Row 3 Col 1	Row 3 Col 2	Row 3 Col 3